## SUMMARY OF SSA MERGER
SSA MERGER( DUE DATE 01.06.2019)
Before Merger |  | Merger |  |  |  | After Merger
|  | Merging SSA |  | Merged SSA
SSA | NAME | SSA | NAME | SSA | NAME |  | SSA | NAME
2401 | MH circle | 2403 | AKOLA | 2404 - AMRAVATI |  |  | 2401 | MH circle
2402 | AHMEDNAGAR | 2431 | YEOTMAL |  |  |  | 2402 | AHMEDNAGAR
2403 | AKOLA | [5 empty] | 2404 | AMRAVATI
2404 | AMRAVATI | 2406 | BEED | 2402 - AHMEDNAGAR |  |  | 2405 | AURANGABAD
2405 | AURANGABAD | [5 empty] | 2409 | CHANDRAPUR
2406 | BEED | 2408 | BULDANA | 2405 - AURANGABAD |  |  | 2412 | JALGAON
2407 | BHANDARA | 2413 | JALNA |  |  |  | 2414 | KALYAN
2408 | BULDANA | [5 empty] | 2415 | KOLHAPUR
2409 | CHANDRAPUR | 2410 | DHULE | 2412 - JALGAON |  |  | 2417 | NAGPUR
2410 | DHULE | [5 empty] | 2418 | NANDED
2411 | GADCHIROLI | 2411 | GADCHIROLI | 2409 - CHANDRAPUR |  |  | 2419 | NASIK
2412 | JALGAON | 2407 | BHANDARA |  |  |  | 2421 | PANAJI
2413 | JALNA | 2430 | WARDHA |  |  |  | 2423 | PUNE
2414 | KALYAN | [5 empty] | 2427 | SATARA
2415 | KOLHAPUR | [5 empty] | 2429 | SOLAPUR
2416 | LATUR | 2416 | LATUR | 2418 - NANDED |  |  | TOTAL | 15
2417 | NAGPUR | 2422 | PARBHANI
2418 | NANDED
2419 | NASIK
2420 | OSMANABAD | 2420 | OSMANABAD | 2429 - SOLAPUR
2421 | PANAJI
2422 | PARBHANI | 2424 | RAIGAD | 2414 - KALYAN
2423 | PUNE
2424 | RAIGAD | 2425 | RATNAGIRI | 2415 -KOLHAPUR
2425 | RATNAGIRI | 2428 | SINDHUDURG
2426 | SANGLI
2427 | SATARA | 2426 | SANGLI | 2427 - SATARA
2428 | SINDHUDURG
2429 | SOLAPUR
2430 | WARDHA
2431 | YEOTMAL

## General
Sl. No. | Activity | Activity Description | Ownership | Template | Tentative Completion Date (N = 31.05.2019)
1 | Formation of Overall Circle SPOC | On behalf of Circle, a DGM level Officer to be nominated as Overall SPOC for entire activities. | Circle | NO | Immediate
2 | Formation of Module wise Circle SPOC | On behalf of Circle, DE/SDE/JTO level Officer to be nominated as Module wise SPOC for entire Module activities. | Circle | NO | Immediate
3 | Template Activity Creation | On ERP Help Desk portal, activities to be created by Core team | Core Team | NO | N-20
4 | Inbox Clearance | All workflows in Inbox (SBWP/UWL)of all Executives of Old BA especially Claim & CSC officers to be cleared before start of blackout. T-code – “ZWFMON” to be used to check pending workflows in Inbox of executives. | Circle | NO | N

## Basis
Sl. No. | Activity | Activity Description | Ownership | Template | Tentative Completion Date (N = 31.05.2019)
1 | SLOC wise role creation (MM, SD, FI) | SLOC wise role creation (MM, SD, FI) | SAP | NO | N-10
2 | Additional Roles | Additional Roles required to SPOCs or any other Executive may be communicated through PIS on ERP Help Desk Portal | Circle | Yes | N-5
3 | Assignment of Role and authorization | Assignment of Role and authorization in new BA to the users of old BA. | Core Team | No | N
4 | De assignment of Role and authorization | De assignment of Role and authorization in old BA to the users of old BA. | Core Team | No | N+5
5 | Authorisation for BDC Balancesheet Item uploading to Circle | ZFI_BUS_POST_MGR_BLK_PST_XXXX xxxx= company code | FICO Core Team | NO | N-1

## FICO
2019-05-31
Sl. No. | Activity | Activity Description | Ownership | Template | Tentative Completion Date (N = 31.05.2019) | DUE DATE | Owner | Template To be Provided BY | Template Name
1 | Temporary Advance - Approval | All Temporary Advances meeting the requirement of that month must be approved by 15 days before commencement of Blackout period. | Circle | NO | N-15 | 2019-05-16 | SSA | NA
2 | Electricity/Generator Meter Master Idetification & creation | Meter master pertaing to Old BA to be created in New BA. | Circle | Yes | N-10 | 2019-05-21 | ERP TEAM | ERP TEAM | NA
3 | Petro/Child card Idetification & Creation | Petro/Child card master pertaing to Old BA to be created in New BA. | Circle | Yes | N-10 | 2019-05-21 | ERP TEAM | ERP TEAM | NA
4 | Creation of cost centres in New BA, if required | Creation of cost centre pertaining to Old BA in New BA, if required | CoreTeam | NO | N-10 | 2019-05-21 | CORE TEAM | NA
5 | Bank account & PMS details | Bank account details in FT-11 template & PMS details in FT-19 template to be informed to FICO core Team through e-mail | Circle | Yes | N-2 | 2019-05-29 | ERP TEAM+ BANKING | SSA | FT-11 & F-19 see on erp helpdesk
6 | Temporary Advance - Settlement | All Temporary Advance Settlement must be completed before commencement of Blackout period. | Circle | NO | N-1 | 2019-05-30 | OLD BA | NA
7 | Mapping of Z Tables for collection | ZFI010 (FT19) to be updated. | SAP | No | N-1 | 2019-05-30 | SAP | NA
8 | SD collections to be remitted to bank | All S&D related collections in old BA should be remitted to bank through ZFI009 or ZFI011 | Circle | NO | N-1 | 2019-05-30 | OLD BA | NA
9 | FBCJ balances to be remitted to bank | Collections posted in FBCJ directly and posted through ZFI017 and ZFI009 should be remitted to bank and should be posted in FBCJ before the start of black out. | Circle | NO | N | 2019-05-31 | SSA | NA
10 | Release to accounting of SD invoices and clearing therof | All Billing Documents of old BAs should be released to accounting and cleared. | Circle | NO | N | 2019-05-31 | SSA | NA
11 | GR/IR etc., Migration | The Balance in GR/IR/Freight Clearing/Cenvat Clearing/Octroi Clearing GL are to be settled as open GR/IR items migration is not possible. | Circle | NO | N | 2019-05-31 | SSA | NA
12 | AUC / CWIP | 1. Balances against AUC should b capitalised as much as possible and remaining amount should be transferreed from Old BA to New BA by taking the WBS of New BA. 2. CJ88 to be executed so that balnce of AUC gets Zero. | Circle | Yes | N | 2019-05-31 | ERP TEAM | SSA
13 | Balance in Clearing GLs and Month End Activities | The balances in all Clearing GLs have to be Zero. All month end activities to be performed. | Circle/BA | No | N | 2019-05-31 | SSA | NA
14 | Clearing of Customers/Vendors/GL | All Customers/Vendors/GL clearing is to be done; otherwise migration of data will be very cumbersome. Since Payment is being made centrally by Circle, if Clearing is not done reconciliation will be a huge task after migration. | Circle/BA | No | N | 2019-05-31 | ERP TEAM | NA
15 | Time Barred Cheques | All Time Barred cheques should be written back immediately, After Migration, Time barred cheque in respect of Old BA which is merged have to be done manually by the Circle BR Team to merged BA | Circle/BA | No | N | 2019-05-31 | ERP TEAM | NA
16 | Employee Vendors Liabilities | All Existing Employee Vendors Liabilities should be reviewed and if any Employee has been transferred to another Circle, AT should be raised immediately. | Circle/BA | No | N | 2019-05-31 | HCM TEAM | NA
17 | TR Refund | The TR Refund new Vendor Mapping in SAP will be done by Core team. | Core Team | No | N | 2019-05-31 | CORE TEAM | NA
18 | Remittance | All Remittance transactions are to be updated in IBTMS. All Intra Circle Remittance transactions between the SSAs which are to be merged should be reconciled | Circle/BA | No | N | 2019-05-31 | ERP TEAM+ATD TEAM | NA
19 | Migration of Inventory | As the Inventory to be transferrred through STO route in which zero balance account get afftected, hence these inventories are to be transferred on last day of TB | Circle | NO | N | 2019-05-31 | ERP TEAM | NA
20 | Banking Item Transfer - Data Provisioning | As the Same Bank GL is to be continued with the changed BA, for this following activity is required to be done beforehand. a) Bank remittance should be updated viz CDR collection, SD Collections, FBCJ Balnace b) BRS should be completed before freezing of TB c) Banking items transfer from Bank GLs to Migration GL is to be done through ZFI236 template | Circle | YES | During Virtual Blackout |  | ERP TEAM | SSA | ZFI236 see on erp helpdesk
21 | Banking Item Transfer - removal of Old BA Bank Account (FT11) data in ZFI138 in Old BA | After completeion of activities at sl. No. 20 Circle will inform Core team for updation change of BA data | SAP | NO | During Virtual Blackout |  | CORE TEAM | NA
22 | Banking Item Transfer - Data Transfer in New BA | After completeion of activities at sl. No. 21 Banking data will be migrated in New BA using template ZFI236. | Circle | YES | During Virtual Blackout |  | ERP TEAM | SSA | ZFI236 see on erp helpdesk
23 | Old Business Area MUST ensure correctness of TBl balances after migration data transaction will get break and reversal will not be possible for example CENVAT etc | Old Business Area MUST ensure correctness of TBl balances after migration data transaction will get break and reversal will not be possible for example CENVAT etc | Circle | NO | N+3 | 2019-06-03 | ERP TEAM | NA
24 | Asset depreciation | Depreciation of assets to be migrated to new BA should be accounted in OLD BA upto Last date of the month. | Circle | NO | N+3 | 2019-06-03 | ERP TEAM | NA
25 | Asset migration | Assets pertaining to Old BA to be migrated (BA & Cost centre Change w.e.f. First day of migration month) after depreciation run in Old BA. | Circle | No | N+3 | 2019-06-03 | ERP TEAM | NA
26 | SAP sundry debtors transaction migration | All the balances related to the SAP sundry debtors transaction of Old BA is to be transferred from Old BA to New BA e.g. Sundry debtors, ST, Security deposits etc. By using template ZFI238/ZFI240 | Circle | Yes | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI238/ZFI240 see on erp helpdesk
27 | Subscriber transaction migration | All the balances related to the subscriber of Old BA is to be transferred from Old BA to New BA e.g. Sundry debtors / ST payable recoverable, Security deposits etc. By using template ZFI236 | Circle | YES | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI236see on erp helpdesk
28 | Revenue Balances migration | Revenue Balances migration from Old BA to New BA by using template ZFI236 | Circle | Yes | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI236 see on erp helpdesk
29 | Expenditure Balances migration | Expenditure Balances migration from Old BA to New BA by using template ZFI236 | Circle | Yes | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI236 see on erp helpdesk
30 | Current asset Balances other Than Reconcilliation GL | Current asset Balances other Than Reconcilliation GL from Old BA to New BA by using template ZFI236 | Circle | Yes | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI236 see on erp helpdesk
31 | Current asset Balances with Reconcilliation GL i.e. Customer open items | Current asset Balances with Reconcilliation GL from Old BA to New BA by using template ZFI238 | Circle | YES | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI238 see on erp helpdesk
32 | Current asset Balances with Reconcilliation GL of special GL indicator i.e. Customer open items | Current asset Balances with Reconcilliation GL from Old BA to New BA by using template ZFI240 | Circle | YES | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI240 see on erp helpdesk
33 | Liability Balances other Than Reconcilliation GL | Liability Balances other Than Reconcilliation GL from Old BA to New BA by using template ZFI236 | Circle | Yes | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI236 see on erp helpdesk
34 | Liability Balances with Reconcilliation GL i.e. Vendor Open items | Vendor Open items with reconcilliation GL will be maintatined through template ZFI238 | Circle | YES | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI238 see on erp helpdesk
35 | Liability Balances with Reconcilliation GL of soeciak GL indicator i.e. Vendor Open items | Vendor Open items with reconcilliation GL will be maintatined through template ZFI240 | Circle | YES | N+3 | 2019-06-03 | CA TEAM | SSA | ZFI240 see on erp helpdesk
36 | Workflow on Vendor Liabilities | The Vendor Liability in case of merged BA will be migrated with Claims officer user id. | Circle/BA | No | N+3 | 2019-06-03 | SSA | NA
37 | One Time customers/Vendors | Balnace in One time customers / Vendors should be zero | Circle/BA | NO | N+3 | 2019-06-03 | SSA | NA
38 | Electricity/Generator Meter Master Closure | Meter master pertaing to Old BA to be closed in Old BA. | Circle | NO | N+10 | 2019-06-10 | ERP TEAM | NA
39 | Petro/Child card Closure | New Petro/Child card master pertaing to Old BA to be closed in Old BA. | Circle | No | N+10 | 2019-06-10 | ERP TEAM | NA
40 | Vendor Payments | No Payments of Open Items related to Old BA to be made in Old BA after start of blackout | Circle | No | After Virtual Blackout |  | CSC TEAM | NA
41 | Statuatory Payments | Circle will pay statutory liability for whole of the circle (including old BA) through FB50 and after complete migration, circle will clear the line items. After migration is over, next month onwards circle will make payment with reference to open item (F-53)/process | Circle | YES | As per due date of statuory payments |  | CSC TEAM
42 | Inbox Clearance | All workflows in Inbox (SBWP/UWL)of all Executives of Old BA especially Claim & CSC officers to be cleared before start of blackout. T-code – “ZWFMON” to be used to check pending workflows in Inbox of executives. | Circle | NO | N | 2019-05-31 | SSA | NA | NA

## HCM
Sl. No. | Activity | Activity Description | Ownership | Template | Tentative Completion Date (N = 31.05.2019)
1 | Reporting Change | Reporting Change of SSA Head, if any | Circle Team | NO | N
2 | Change of cost centre against Position | Association of new BA cost centres with all positions (Including Look after, Vacant positions) | Core Team | NO | N+2
3 | Change of cost centre in HRP1018 | Change of cost centre in HRP1018 for already maintained positions | Core Team | NO | N+2
4 | Change of in Account assignment | Change of PA/PSA/BA/CC in Account assignment (HRP1008) for all positions (Including Look after, Vacant positions) | Core Team | NO | N+2
5 | Change in PA0001 for BA | Change in BA in IT0001 | Core Team | NO | N+2
6 | Change in IT27 for Cost center' | Change in BA/ CC in IT0027 | Core Team | NO | N+2
7 | Changes in Table ZHRTR_PSA_BA | Changes in Table ZHRTR_PSA_BA | Core Team | NO | N+2
8 | Assignment of Role and authorization | Assignment of Roles in new BA to the users of new BA/Old BA as per requirement. | Circle/Core Team | Yes | N
9 | De assignment of Role and authorization | De assignment of Roles in old BA from the users of old BA as per requirement. | Circle/Core Team | Yes | N+10

## MM
Sl. No. | Activity | Activity Description | Ownership | Template | Tentative Completion Date (N = 31.05.2019)
1 | Creation of SLOC in New BA | Creation of SLOCs pertaining to Old BA in New BA | SAP/MM Core Team* | No | N-15
2 | Identification of material codes for Extension in New BA | Identification of material codes for Extension in New BA - MM02 (new Material creation sheet) | MDM MM Core team/SAP* | No | N-10
3 | Extension of material codes in New BA/SLOC | All material of Old BA to be extended in New BA - MM02 (new Material creation sheet) | MDM MM Core Team/SAP* | No | N-5
4 | Block of Material Master Data for Plant | Maintain Plant block in Material master for Old BA | MDM MM Core Team/SAP* | No | N+2
5 | Punching of Open GRs | All inventories where GR/IR is pending, needs to be posted in ERP. This activity has to be carried out by L2/L1 team of Circle users under guidance of core team | Circle | No | N-2
6 | MIRO of PO with SES/MIGO (No MIRO cases) exclusively for Old BA | MIRO to be done by Old BA | Circle | No | N-2
7 | Identification of PO with Partial SES/MIGO,Open Reservations, PR's, PO's and STO's to be Short Closed/closed in old plants as the case may be. | Identification & Short close/close by Old BA. [All inventories where GR/IR is pending, needs to be posted in ERP. This activity has to be carried out by L2/L1 team of Circle users under guidance of core team] | Circle | No | N-1
8 | Creation of PO with Partial SES/MIGO in New BA | Creation of New PO with residual qty/value in New BA | Circle | No | After end of Virtual blackout i.e. post go live period
9 | Transfer of saleable stock | Transfer of stock by Movement type 301 by Circle L2 Team. Delay in this activity will increase the Virtual blackout for SD sales. | Circle | NO | N
10 | SIT (Stock in TransiT)to be reconciled before merger | All SIT stock to be nil in old plants before merger. SIT stock to be either received in receiving location or issueed material document to be cancelled at origin plant. | Circle | No | N-1
11 | Transfer of stock (Other than Saleable) | Transfer of stock by Movement type 301 by Circle L2 Team | Circle | No | N+1
12 | Issue of Inventory (other than Saleable) during Virtual Blackout | Inventory during Virtual Blackout to be issued out of SAP and it should be updated in ERP after migration. | Circle | No | After end of Virtual blackout
13 | Updation of ref circle z table | Maintaining new plants in ref circle z table of MM module | Core Team / SAP | No | N+1
14 | Plant Level Authorization Role Changes (Assignment) | Derived Role Changes for Purchase Requisition, inventory management , PO and SES[New roles for the post merger scenario will be assigned to related users on "N". Further old roles for pre merger mm entities(plant, sloc etc.) will remain assigned upto N+2 so as to complete inventory transfer transactions from old destination in pre merger scenario to new post merger destination. Subsequent to this, old roles will be restricted to use.) | Core Team / SAP | No | N+1
15 | STO configuration updation | Shipping data configuraiton to be updated for STO for triggering relevant shipping point | SAP | No | N-1

## PM
Sl. No. | Activity | Activity Description | Ownership | Template | Tentative Completion Date (N = 31.05.2019)
1 | Equipment Master data extraction | Extraction of Equipment Master data (T-code - IH08). | Core Team | No | Immediate
2 | Extraction of existing Open Notifications & Maintenance Orders | Extraction of existing Open Notification & Maintenance Order in old BA (T-Code: IW29,& IW 39 respectively) | Circle/Respective BA/Plant | No | Immediate
3 | Notification & Maintenance Order Closure | Completion, Settlement and closure of all the PM Open Notifications and Maintenance Orders in Old BA. | Circle/Respective BA/Plant | No | N-10
4 | Functional Location Creation | Creation of New FLs (for all SDCAs of SSA in Old BA)as per FL Structure in New BA . (Note: Existing Structure to be modified through Alternative Labelling) | Core Team/SAP | No | N-5
5 | Work Centre Creation | Creation of new Work Centres in new BA corresponding to existing Work Centres of SSAs in Old BA. | Core Team | No | N-5
6 | Bill of Material creation | Creation of new EBOM in new BA corresponding to existing EBOM of SSAs in Old BA. | Core Team | No | N-5
7 | Planner Group Identification | Indentification of Missing Planner groups in new BA. | Core Team | No | N-5
8 | Planner Group Creation | Creation of Missing Planner groups in new BA, if required. | SAP | No | N-5
9 | Functional Location Master data updation | Updation of new BA, New Maintenance Plant, New Planning Plant in New FLs in New BA FL Structire. | Core Team/SAP | No | N+1
10 | Equipment Master data updation | Updation of of Equipment Master data in New BA (Updation of new Cost Centre, new Work Centre, New BA, New Planning Plant, New Maintenance Plant, New Planner Group, | Core Team/SAP | No | N+3 (It depends on FICO Module as the pre requisite for completion of this activity is completion of Asset transfer activity vide sl.No.25 in FICO Module)
11 | Assignment of Role and authorization | Assignment of Role and authorization in new BA to the users of old BA. | Core Team | No | N
12 | Verification of Equipment Master data in New BA | Verification of Migrated PM Master data ( Equipments, Work Centres, Cost Centres etc) in New BA. | Circle | No | Post Go-Live/N+3
13 | PMIS report (Standard Reports of PM Module) | PMIS to be reviewed with New BA | Core Team | No | N+4
14 | De assignment of Role and authorization | De assignment of Role and authorization in old BA to the users of old BA. | Core Team | No | N+5
15 | Deletion of Master Data in Old BA | Deletion (Setting of Deletion flag) of existing unused FLs and Work Centres etc. in Old BA | Core Team | No | N+10

## PS
Sl. No. | Activity | Activity Description | Ownership | Template | Tentative Completion Date (N = 31.05.2019) | Owner
1 | Identification, Capitalisation & Closure of PDs/WBS's pertaining to Old BA wherein Total work is completed. | Circle/Old BA Team to Identify (Tcode-CN41) such PDs/WBS's, Capitalise and close it in ERP in OLD BA. | Circle | No | N-8
2 | Identification, Capitalisation & Closure of PDs/WBS's pertaining to Old BAwherein partial work is done. | Circle/Old BA Team to Identify (Tcode-CN41) such PDs/WBS's, Capitalise and close it in Old BA in ERP, if any. | Circle | No | N-8
3 | Identification & Closure/Deletion of PDs/WBS's pertaining to Old BA wherein no cost has been posted in Old BA. | Circle/Old BA Team to Identify (Tcode-CN41) such PDs/WBS's and close/Delete it in Old BA, if any. | Circle | No | N-8
4 | Data for creation of PDs/WBS's pertaining to Old BA wherein partial work is done and the same could not be capitalized. | For work of balance amount, circle will forward the data in Templates PS-01 to PS08 & PS11 for creation of WBS in New BA. Similar action for CWIP through templates PS-10 and PS-12. | Circle | Yes | N-6
5 | Validation of PDs/WBS's pertaining to Old BA wherein partial work is done and the same could not be capitalized. | Validation of data/templates received for work of balance amount. | Coreteam | No | N-4
6 (a) | Uploading of Data from Templates for PD/WBS/Network, PDF generation and Release of WBS. | Uploading of Data from Templates for PD/WBS/Network, PDF generation and Release of WBS. | Coreteam / SAP | Yes | N-4
6 (b) | IM Node Assignment,Budget Allocation and CWIP Migration | IM Node Assignment,Budget Allocation and CWIP Migration | Circle/FICO | Yes | N
7 | Assignment of Role and authorization | Assignment of Role and authorization in new BA to the users of old BA. | Core Team | No | N
8 | Creation of PDs/WBS's pertaining to Old BA wherein partial work is done and the same has been capitalized. | For Balance amount of work of such WBSs where partial cost has been posted and capitalized in Old BA. For such cases, PD/WBSs are to be created fresh in New BA for balance amount. Circle team to complete creation, approval & further process. | Circle | No | N+3
9 | Creation of PDs/WBS's in New BA pertaining to Old BAwherein no cost has been posted in Old BA. | All the WBS where no cost has been posted in Old BA are to be closed in Old BA and fresh to be created in New BA. Circle team to complete creation, approval & further process. | Circle | No | N+3
10 | De assignment of Role and authorization | De assignment of Role and authorization in old BA to the users of old BA. | Core Team | No | N+5

## REM
Sl. No. | Activity | Activity Description | Ownership | Template | Tentative Completion Date (N = 31.05.2019)
1 | Extraction of departmental RE (Real State) Objects | Identify the BE wise master data for departmental lands, buildings and rental objects which need to be shifted from Old BE to New BE and enlist their details along with existing SAP codes (REM-4 template) | Core Team | YES | N-15
2 | Extraction of Lease Out Contracts | Identify the respective Land & Bldg. lease out/ Staff Quarters Lease out & allotment contracts and enlist the contract numbers with details along with codes of Master Tenant/ Emp. (REM-09/10/11 & REM 16/17/18/19/20/21 /22/23 templates) | Core Team | YES | N-15
3 | Extraction of Leased In RE Objects | Identify the BE wise master data for leased in /rented lands, buildings and rental objects which need to be shifted from Old BE to New BE and enlist their details along with their SAP codes (REM-02/03 templates) | Core Team | YES | N-15
4 | Extraction of Lease In Contracts | Identify the respective Land & Bldg. lease in contracts and enlist the contract numbers with details along with codes of Landlord (REM-12/13/14/15 templates) | Core Team | YES | N-15
5 | Validation of REM master & Transactional data | All the data of REM 02/03/04 & REM09 to REM23 templates need to be validated by core team for uploading | Core Team | YES | N-10
6 | Upload of REM master & Transactional data | All the data REM 02/03/04 & REM12 to REM23 to be uploaded with contracts in inactive state | SAP | YES | N-5
7 | Competing periodic posting for all REM contracts (Lease in and Lease out) upto 'N' date including invoicing for lease out contracts. | Periodic posting for all type of contracts need to be completed upto last day of the month i.e.upto 'N' date and invoicing for lease out contracts also to be completed . | Circle | NO | N
8 | Closing of bookings for IQ/Hostels/CC/Auditorium/Temp. Staff Quarters and posting/ invoicing thereof | Posting against all bookings of IQ/ Hostel/CC/Auditorium/Temp.Staff Quarters need to be completed upto 'N' date. Bookings spanning beyond last month, before migration, also need to be closed and posting carried out against the same upto 'N' date. | Circle | NO | N
9 | Creating new Bookings for bookings spanning beyond 'N' date | New booking should be created against such bookings from next month under new BA (posting upto 'N' to be completed in previous BA as per last point). | Circle | NO | N+7
10 | Land & Bldg. lease out/ SQ Lease out & allotment contract closure | Land & Bldg. lease out/ SQ Lease out & allotment contracts to be closed in Old BE, Contract end date should be the last date of the month previous to migration month. | Circle | NO | N+1
11 | Staff quarter contract closure | Staff quarter contracts (Employees related z800 type) to be closed ( by entering 'possession date to' in term tab also in addition to valid to date) in Old BA. Contract end date should be the last date of the month previous to migration month. | Circle | No | N+1
12 | Land & Bldg. lease In contract closure | Land & Bldg. Lease in contracts to be closed in Old BE, Contract end date should be the last date of the month previous to migration month. | Circle | No | N+1
13 | RE Objects Validity closure (Departmental and Rented both) | Validity of REM objects i.e. Lands, Buildings, Rental objects, which are to be shifted, need to be closed in Old BE with 'Validity to date' as last date of the month previous to migration month. | Circle | NO | N+1
14 | Roles and authorization | Assignement of new roles of new BA, ( except accounting and contract activation roles ) to users to check / append data | REM, BASIS core/ SAP | YES | N
15 | Data Verification in New BE | Checking of uploaded master data and transactional data in new BE and updating the same in ERP i.e. any land/bldg./RO/Contract not uploaded (created after data extraction by core team) also need to be created in system. | Circle | NO | Post Go-Live
16 | Contracts activation after data verification | After the data is varified by circle the contracts shall be activated for further posting | SAP | NO | Post Go-Live
17 | Roles and authorization | Assignment of additional activation/ accounting roles to users to carry out accounting transactions including postings / invoicing /reversal of posting and Deassignment of old roles. | REM,BASIS core / SAP | YES | Post Go-Live after verification of data
18 | De assignment of Role and authorization | De assignment of Role and authorization in old BA to the users of old BA. | Core Team | No | N+5

## SD
Sl. No. | Activity | Activity Description | Ownership | Template | Tentative Completion Date (N = 31.05.2019)
1 | Identification of POI exchanges data of old BA | POI Exchange Data in SD20 Tempalte shall be provided by Circle. | Circle | YES | N-10
2 | Upload of Sales office in POI exchanges Master data of Old BA | upload of Sales office in POI exchanges Master data of old BA in new BA | Core Team | No | N-2
3 | Identification of POI sales order pertaining to old BA | Identification of POI sales order pertaining to old BA and to be provided in SD 24 Template. | Circle | Yes | N-10
4 | Change of Sales Office in POI Sales Order pertaining to old BA | Change of Sales Office in POI Sales Order pertaining to old BA in new BA | SAP/ Core Team | No | N+1
5 | Identification of Storage Location Mapping | Idendification of Storage Locatrion Mapping in old BA and provide the same data corresponding to SLOCs in new BA in SD 34 template. | Circle | YES | N-2
6 | Upload of Storage Location Mapping | Uploading of Storage Location Mapping data corresponding to SLOCs in new BA. | Core Team | NO | N+1
7 | Change of Plant/SLOC/Customer Mapping of old BA, in New BA | Plant/SLOC/Customer Mapping ( Template SD32) mapping to be modified for the chanel partner and One Time customers by L2 SPOC of Circle. | Circle | YES | N+1
8 | Provision of CSC C TOPUP Open Sales Orders Data in SD42 | Provision of Data in template SD42 by Circle L2 / CCNO | Circle | YES | N
9 | Change of sales office in CSC C TOPUP sales order provided in SD42 template | Change of sales office in CSC C TOPUP sales order data provided in SD42 | SAP/Core Team | No | N+1
10 | Idendification and Change of Sales office in Channel Partner Customer Master | Change of New Sales Office & Plant to be maintained in all Channel Partner customers. | Core Team | No | N+1
11 | Change of Sales office in One Time Customer Master | New Sales Office & Plant to be maintained in all One Time customers. | Core Team | No | N+1
12 | Plant / Shipping Point / Sales office Level Authorization Role of new BA to be assigned to users of old BA | Plant / Shipping Point / Sales office Level Authorization Role of new BA to be assigned to the users of old BA | Basis Core Team / SAP | No | N
13 | Plant / Shipping Point / Sales office Level Authorization Role in old BA to be removed | Plant / Shipping Point / Sales office Level Authorization Role in old BA to be removed | Basis Core Team / SAP | No | N+4
14 | Creation of New SLOCs of old BA under new BA. | Creation of New SLOCs of old BA under new BA. | MM Core Team | YES | N-15
15 | All Stocks in the SLOCs of old plants ( old BA) to be moved to respective SLOCs of new Plants (New BA) | All Stocks in the SLOCs of old plants ( old BA) to be moved to respective SLOCs of new Plants (New BA) | Circle | No | N