## SUMMARY
OFC & OF Equip. Commissioning during F.Y.2019-20
OFC (Commissionig) |  |  | OF Equipment
Development | 242 | Km* | A1 CPAN | 1250 | Nos
Rehabilitation | 136 | km | A2 | 8 | Nos
Mntc | 576 | Km | B1 | 114 | Nos
Total | 954 |  | B2 | 123 | Nos
|  | MADM-16# |  | 10
|  | ADM/CPE# |  | 151
OFC Target : 2019-20: 1000 km
242 KM*: Utilized for EB Cases /58 km for GSM (Phase-VIII)
136 Km : Rehabilitation work(Before 30.06.2019)
OFC & OF Equip. Commissioning during F.Y.2018-19
OFC (Commissionig) |  |  | OF Equipment
Development | 781 | Km* | A1 CPAN | 900 | Nos
Rehabilitation | 253 | km | A2 | 9 | Nos
Mntc | 670 | Km | B1 | 47 | Nos
Total | 1704 |  | B2 | 25 | Nos
|  |  | MADM-16 | 33 | Nos
|  |  | ADM/CPE | 162 | Nos
OFC Target : 2018-19: 1500 km
Rehabilitation Target : 2018-19: 2500 km

## Commd. 2018-19
Annexure-I
Status of OFC Commissioned in 2018-19 as on 31.03.2019
Sl no | SSA | Commissinoned in F.Y.2018-19 | [12 empty] | OFC used for Mtce. from 01.04.18 to 31.03.19 (24/48/96 F) | OFC used for Rehabitation. from 01.04.18 to 31.03.19
|  | Apr. 2018 | 2018-05-01 | June2018 24/48F | July 2018 24/48F | Aug2018 24/48/96 F | Sep 2018 24/48/96 F | Oct 2018 24/48/96 | Nov 2018 24/48/96F | Dec 2018 24/48/96F | Jan 2019 24/48/96F | Feb 2019 24/48/96F | 2019-03-01 | Total
1 | Ahmednagar | 0.65 | 1.526 | 1.3 | 0 | 3 | 3.6 | 1.46 | 1.96 | 7.7 |  | 1.9 | 1.12 | 23.096 | 28.73 | 13.3
2 | Amravati | 0 | 0 |  | 7.9 | 4 | 0 |  | 20 | 0 |  | 32.26 |  | 64.16 | 12.19 | 0
3 | Akola | 3 | 0 | 1.4 | 1 | 0 | 0 | 0 | 0 | 7.3 |  | 4.49 | 5.77 | 17.19 | 16.77 | 15.2
4 | Aurangabad | 1.01 | 2.26 | 2.9 |  | 41.38 |  |  |  |  | 36.65 | 5.28 | 52.33 | 89.48 | 42.04 | 3
5 | Beed | 3.077 | 0 | 14.12 | 0 | 0.4 | 12.5 | 0 | 2.3 | 3 |  | 0.93 | 0.82 | 36.327 | 21.425 | 0.5
6 | Bhandara | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 | 5 | 0
7 | Buldana | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 18.65 |  |  | 18.65 | 5.23 | 0
8 | Chandrapur | 17 | 0 | 0 | 1.5 | 0 | 0 | 0 | [5 empty] | 18.5 | 1.65 | 0
9 | Dhule | 0 | 1.88 | 0 | 0 | 1.296 | 9.24 |  |  |  |  | 12.39 |  | 24.806 | 18.75 | 14.98
10 | Gadchiroli | 0 | 0 | 0 | 19.57 | 0 | 0 | 15.74 |  |  |  | 5.16 |  | 40.47 | 6.25 | 9.3
11 | Goa | 0 | 1.534 | 0 | 0 | 0 | 0.2 | 1.2 | 0.74 | 0 |  | 0 | 0.07 | 3.674 | 22.618 | 0
12 | Jalgaon | 26.342 | 0 | 34.47 |  | 0 |  |  | 11.85 |  |  | 3.73 | 16.26 | 76.392 | 27.404 | 0
13 | Jalna | 0 |  | 0 |  |  |  | 0 |  | 0 | 17.49 |  |  | 17.49 | 19.45 | 0
14 | Kalyan | 0 | 0 | 6 | 0 | 0 | 0 | 6.66 | 0 |  | 0 | 0 |  | 12.66 | 17.41 | 11.062
15 | Kolhapur | 0.1 | 8.99 | 15.54 | 0 | 0 | 0.5 | 26.25 | 20.36 |  | 0 | 0 |  | 71.74 | 24.087 | 43.54
16 | Latur | 0 | 0.15 | 0.62 | 0 | 0 | 0 |  |  |  |  | 2.15 |  | 2.92 | 15.447 | 0
17 | Nagpur | 3 | 2 | 6.15 | 0 | 0 | 2 | 10.05 | 1.8 | 0 |  | 10.3 | 2.195 | 35.3 | 38.56 | 23.184
18 | Nanded | 0 | 0 | 0 | 0 | 7.404 | [5 empty] | 2.6 |  | 10.004 | 9.84 | 0
19 | Nashik | 0 | 12.22 | 0.15 | 0 | 0 | 1.9 | 1.5 | 6.1 | 2.45 |  | 10.34 | 0.798 | 34.66 | 23.5 | 35.15
20 | Osmanabad | 0 | 0 | 0 |  | 0 | [6 empty] | 13.731 | 0 | 24.269 | 0
21 | Parbhani | 1.5 | 0 | 0 | 0.7 | 0 | [6 empty] | 7.61 | 2.2 | 10.903 | 2.1
22 | Pune | 1.7 | 0 | 25.67 | 3.71 | 2.26 |  | 4.73 | 2.65 | 1.6 | 0 | 0 | 14.81 | 42.32 | 51.56 | 40
23 | Raigad | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 14.28 | 0 | 37.4 | 21
24 | Ratnagiri | 0 |  |  | 35.4 | 0 | 0 | 0 | 0 |  |  |  |  | 35.4 | 4.549 | 0
25 | Sangli | 0 | 0 | 0 | 0 | 4.4 | 0 | 0 | 0 | 0 |  |  | 0.25 | 4.4 | 17.65 | 14
26 | Satara | 0 | 0 | 0 | 0 | 0 |  | 0 | 7.377 | 0 |  | 1.53 |  | 8.907 | 21.05 | 0
27 | Sindhudurg | 0 | 0 | 1.67 | 0 | 19.721 | 0 |  | 0 |  |  | 0.86 |  | 22.251 | 26.9 | 0
28 | Solapur | 0 | 0 | 0 |  |  | 67.84 |  | 0 |  |  |  |  | 67.84 | 8.462 | 3
29 | Wardha | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 74.882 | 5
30 | Yeotmal | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 36.525 | 0
| Total: | 57.379 | 30.56 | 109.99 | 69.78 | 83.861 | 97.78 | 67.59 | 75.137 | 22.05 | 72.79 |  | 130.044 | 780.837 | 670.501 | 254.316
|  |  | 24F | 48F | Total
| Dovelopment |  | 697 | 84 | 781
| Maintenance |  | 517 | 153 | 670
| Rehabitation |  | 238 | 15 | 253
1704

## Commd. 2019-20
OFC & OF Equipment Commissioning (01.04.2019 to 31.03.2020)
Sr. No. | SSA NAme | Development |  |  |  | Rehab | Mntc | OF Equipment (CPAN) |  |  |  | OF Equipment any other
|  | 24F | 48F | 96F | Total |  |  | A1 | A2 | B1 | B2 | ADM-1/CPE | ADM-16
1 | Ahmednagar | 0 | 3.6 | 0 | 3.6 | 2.03 | 32.42 | 60 | 2 |  |  | 46 | 2
2 | Akola | 0 | 0 | 0 | 0 | 0 | 16.95 | 9 | 0 | 4 | 1 | 18
3 | Amravati | 0 | 11.562 | 0 | 11.562 | 24 | 21.445 | 75 | 0 | 6 | 6 | 0
4 | Aurangabad |  |  |  | 0 |  |  | 88 |  | 1 | 13
5 | Beed | 0 | 1.1 | 0 | 1.1 | 1.06 | 14.44 | 47 | 0 | 0 | 0
6 | Bhandara | 33 | 0 | 0 | 33 | 46 | 27 | 74 | 0 | 0 | 9 | 14 | 4
7 | Buldhana | 11.4 | 3.4 | 0 | 14.8 | 0 | 18.4 | 24 | 0 | 4 | 4 | 0
8 | Chandrapur | 9.51 | 0 | 0 | 9.51 | 1.85 | 4.45 | 53 | 0 | 0 | 0 | 0
9 | Dhule | 0 | 0 | 0 | 0 | 0 | 4.5 | 5 | 0 | 0 | 0 | 0
10 | Gadchiroli | 0 | 0 | 0 | 0 | 0 | 3.6 | 6 | 0 | 0 | 0 | 0
11 | Goa | 0 | 20.4 | 0 | 20.4 | 0 | 12.1 | 65 | 0 | 0 | 0
12 | Jalgaon | 1.68 | 0 | 0 | 1.68 | 0 | 37.334 | 37 | 0 | 0 | 8 | 0
13 | Jalna | 0 | 0.065 |  | 0.065 |  | 2.45 | 20 |  | 3 | 5
14 | Kalyan | 0 | 0.4 | 0 | 0.4 | 5.55 | 48.05 | 21 |  | 3 | 3
15 | Kolhapur | 7.033 | 0 | 0 | 7.033 | 7.061 | 17.935 | 40 | 0 | 0 | 1 | 45
16 | Latur |  |  |  | 0 |  | 2.85 | 20 |  | 8 | 4
17 | Nagpur | 0 | 0.43 | 0 | 0.43 | 9.6 | 27.039 | 86 | 0 | 0 | 0 | 0
18 | Nanded | 0 | 0 | 0 | 0 | 0 | 24.641 | 16 | 0 | 11 | 3 | 0
19 | Nasik | 11.73 | 9.98 |  | 21.71 |  | 28.3 | 52 |  | 13 | 8
20 | Osmanabad |  |  |  | 0 |  |  | 35 |  | 6 | 4
21 | Prabhani | 0 | 8.075 | 0 | 8.075 | 0 | 8.08 | 8 |  |  |  | 0
22 | Pune | 30.51 | 18.45 | 3.85 | 52.81 | 30 | 58 | 62 |  | 21 | 24 | 28 | 4
23 | Raigad | 0 | 5.537 | 0 | 5.537 | 0 | 32.234 | 22 | 0 | 8 | 6 | 0
24 | Ratnagiri | 0 | 0 | 0 | 0 | 0 | 10 | 61 | 0 | 8 | 8 | 0
25 | Sangli | 0 | 0 | 0 | 0 | 6.82 | 15.01 | 47
26 | Satara | 3.765 | 0 | 0 | 3.765 | 0 | 17.346 | 59 | 5 | 0 | 0 | 0
27 | Sindhudurg |  | 5.05 |  | 5.05 |  | 14.1 | 33 |  | 5 | 2
28 | Solapur | 8.8 | 24.56 | 0 | 33.36 | 2.146 | 56.95 | 78 | 1 | 8 | 6
29 | Wardha | 0 | 0 | 0 | 0 | 0 | 13.43 | 14 |  | 5
30 | Yeotmal | 4 | 4 |  | 8 | 0 | 7.15 | 33 |  | 0 | 8
| Total | 121.428 | 116.609 | 3.85 | 241.887 | 136.117 | 576.204 | 1250 | 8 | 114 | 123 | 151 | 10
Note on D11: ====== ID#AAAAGX_nVJo SDE TRANS BULDANA (2020-04-06 01:19:04) Overhead Cable Erected for stable Ring Connectivity of Buldhana District Place
Note on E11: ====== ID#AAAAGX_nVJs SDE TRANS BULDANA (2020-04-06 01:19:35) Cable Laid for DoJ Circuits